Board of Accreditation (BOA)

Department of Social Work Accreditation (DOSWA)

Baccalaureate and Master’s Social Work Program Accreditation

Timetable for Candidate Programs

June 2025 – June 2027 Agenda | Retroactive Accreditation to Fall 2024

# Choosing a Timetable:

Begin the candidacy planning process by identifying when the program plans to admit its first students into its social work program (if it is intended that these students would be under the program’s retroactive accreditation). This will assist in determining the academic year in which the program will plan to be granted candidacy status, which then determines which timetables to follow. Once a timetable is chosen by a program, it is suggested that the program review the activities, dates, and submission instructions to determine the steps necessary to be eligible for the selected timetable. Note: The program can plan for a certain agenda, however assignment to an agenda is not guaranteed. A maximum of ten (10) programs are reviewed for a Candidacy decision at each Board of Accreditation (BOA) meeting. Once ten (10) pre-candidate programs are assigned to a BOA meeting agenda, the subsequent programs will automatically be assigned to the next available BOA meeting agenda (per policy 5.3 Assignment to a BOA Meeting Agenda in the Accreditation Policy Handbook).

Timetable to Pre-Candidacy Status

| Activity or Document | Date | Submission Instructions |
| --- | --- | --- |
| Program attends Drop-In Group Consultations with CSWE Staff (optional) | # Every two (2) weeks | N/A |
| Program prepares to submit Candidacy Eligibility Application: - Institutional approval and supports - Regional accrediting body approval (if applicable) - Appropriate state, district, or territory-level higher education authority approval (if applicable) | # Prior to submitting the Candidacy Eligibility Application | N/A |
| Review the Faculty Hiring Grid for more information. | # Prior to submitting the Candidacy Eligibility Application | N/A |
| Program submits Candidacy Eligibility Application | # On a rolling basis* # *At least 30 days prior to planned submission of the program’s Benchmark 1 documents for staff approval | The program emails the application to accreditation@cswe.org |
| Program submits Candidacy Eligibility Fee | On a rolling basis* *Candidacy eligibility fee must be received prior to candidacy eligibility application approval | Follow directions on the Candidacy Eligibility Application Direct fee or invoice questions to feesaccred@cswe.org |
| CSWE staff approves Candidacy Eligibility Application | # Within 30 days of submission | N/A |
| - At least two (2) full-time faculty hired with principal assignment (51% or more) to the program that is seeking candidacy, with a start date no later than 30 days prior to candidacy visit 1 - The program director role hired, with a start date no later than 30 days prior to candidacy visit 1 - The field director role hired, with a start date no later than 30 days prior to candidacy visit 1 See Faculty Hiring Grid for more information | # Prior to submitting the Benchmark 1 for Staff Approval | N/A |
| # Program submits Benchmark 1 documents for staff approval (Volumes 1, 2, and 3) using the Required Benchmark 1 Template for Volume 1 and using the 2022 Interpretation Guide to provide guidance for developing clear and concise written compliance narratives | On a rolling basis* *Submitting the document 6-months in advance (March 1, 2024) is a best-practice, not a required due date. | The program emails the application to the Director of Accreditation Operations |
| # CSWE staff review and provide iterative feedback on Benchmark 1 until approval # CSWE staff approve Benchmark 1 and places program on an agenda for Candidacy Review - Program is granted Pre-Candidacy status - Program is added to the Directory of Accredited Programs - Program is assigned an Accreditation Specialist | On a rolling basis* # *First 10 Benchmark 1 documents approved by September 1, 2024, are placed on June 2025 BOA Agenda for candidacy review with a retroactive accreditation date of Fall 2024. (Next 10 Benchmark 1 documents approved are placed on October 2025 BOA Agenda, which has a retroactive accreditation date of Fall 2025.) | N/A |

Timetable to Candidacy Status

| Activity or Document | Date | Submission Instructions |
| --- | --- | --- |
| CSWE invoices program for the Candidacy Visit 1 Fee via email | September 1, 2024 | N/A |
| The program pays the Candidacy Visit 1 fee | No later than October 1, 2024 | Direct fee or invoice questions to feesaccred@cswe.org |
| CSWE Staff assigns a BOA member for Candidacy Visit 1 | No later than October 1, 2024 | N/A |
| Program contacts BOA member visitor to begin planning per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Within 2 weeks of visitor assignment | N/A |
| Program and visitor select a visit date and program documents date to CSWE per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | Program submits the Candidacy Visit Date Log |
| The program’s primary contact confirms visit arrangements such as travel plans, hotel accommodations, and workspace requirements in the hotel and on campus (for in-person visits) with the visitor per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | N/A |
| Programs reviewed under the 2022 EPAS submit: Benchmark 1 documents for BOA review (Volumes 1, 2, and 3) using the Required Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 3 Benchmark 1 documents to the BOA member visitor and the program’s CSWE accreditation specialist |
| Programs reviewed under the 2015 EPAS submit: Benchmark 1 documents for BOA review (Benchmark 1 Review Brief, and Volumes 1, 2, and 3) using the Optional Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 4 Benchmark 1 documents to the BOA member visitor and the program’s CSWE accreditation specialist |
| The program’s primary contact and visitor jointly finalize the candidacy visit schedule per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No less than 1-week prior to the visit | N/A |
| Candidacy Visit 1 occurs For more information candidacy visits, review policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Between December 1, 2024 – February 28, 2025 | N/A |
| BOA Member Visitor submits the Candidacy Visit Report per policy 5.10 Candidacy Visits 1, 2, & 3 Reports in the Accreditation Policy Handbook | Within 2 weeks of the last day of the visit | The BOA visitor e-mails visit report to the program’s CSWE accreditation specialist to review, finalize, and forward to the program |
| Program responds to the Candidacy Visit Report policy 5.11 Program Response to the Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | # Within 2 weeks of receiving the Candidacy Visit Report | The program e-mails the Program Response to the program’s CSWE accreditation specialist |
| BOA reviews the program’s Benchmark 1, Candidacy Visit Report, and Program Response to make a candidacy decision Decision types are detailed in policy 5.12 BOA Benchmark 1 Decisions in the Accreditation Policy Handbook | June 2025 BOA Meeting | N/A |
| All BOA letters are issued 30-days after the meeting | July 2025 | N/A |

Timetable to 2nd Year of Candidacy Status

| Activity or Document | Date | Submission Instructions |
| --- | --- | --- |
| CSWE invoices program for the Candidacy Visit 2 Fee via email | July 1, 2025 | N/A |
| The program pays the Candidacy Visit 2 fee | No later than September 1, 2025 | Direct fee or invoice questions to feesaccred@cswe.org |
| CSWE Staff assigns a BOA member for Candidacy Visit 2 | No later than October 1, 2025 | N/A |
| Program contacts BOA member visitor to begin planning per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Within 2 weeks of visitor assignment | N/A |
| Program and visitor select a visit date and program documents date to CSWE per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | Program submits the Candidacy Visit Date Log |
| The program’s primary contact confirms visit arrangements such as travel plans, hotel accommodations, and workspace requirements in the hotel and on campus (for in-person visits) with the visitor per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | N/A |
| Programs reviewed under the 2022 EPAS submit: Benchmark 2 documents for BOA review (Volumes 1, 2, and 3) using the Required Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 3 Benchmark 2 documents to the BOA member visitor and the program’s CSWE accreditation specialist. |
| Programs reviewed under the 2015 EPAS submit: Benchmark 2 documents for BOA review (Benchmark 1 Review Brief, and Volumes 1, 2, and 3) using the Optional Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 4 Benchmark 2 documents to the BOA member visitor and the program’s CSWE accreditation specialist |
| The program’s primary contact and visitor jointly finalize the candidacy visit schedule per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No less than 1-week prior to the visit | N/A |
| Candidacy Visit 2 occurs For more information candidacy visits, review policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Between December 1, 2025 – February 28, 2026 | N/A |
| BOA Member Visitor submits the Candidacy Visit Report per policy 5.10 Candidacy Visits 1, 2, & 3 Reports in the Accreditation Policy Handbook | Within 2 weeks of the last day of the visit | The BOA visitor e-mails visit report to the program’s CSWE accreditation specialist to review, finalize, and forward to the program |
| Program responds to the Candidacy Visit Report policy 5.11 Program Response to the Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | # Within 2 weeks of receiving the Candidacy Visit Report | The program e-mails the Program Response to the program’s CSWE accreditation specialist |
| BOA reviews the program’s Benchmark 2, Candidacy Visit Report, and Program Response to make a candidacy decision Decision types are detailed in policy 5.13 BOA Benchmark 2 Decisions in the Accreditation Policy Handbook | June 2026 BOA Meeting | N/A |
| All BOA letters are issued 30-days after the meeting | July 2026 | N/A |

Timetable to Initial Accreditation

| Activity or Document | Date | Submission Instructions |
| --- | --- | --- |
| Program submits Initial Accreditation Eligibility Application | July 1, 2026 | # The program e-mails application to accreditation@cswe.org |
| CSWE invoices program for the Initial Accreditation Fee via email | November 1, 2026 | # N/A |
| The program pays the Initial Accreditation fee | No later than November 15, 2026 | Direct fee or invoice questions to feesaccred@cswe.org |
| CSWE Staff assigns a BOA member for Candidacy Visit 3 | No later than October 1, 2026 | N/A |
| Program contacts BOA member visitor to begin planning per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Within 2 weeks of visitor assignment | N/A |
| Program and visitor select a visit date and program documents date to CSWE per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | Program submits the Candidacy Visit Date Log |
| The program’s primary contact confirms visit arrangements such as travel plans, hotel accommodations, and workspace requirements in the hotel and on campus (for in-person visits) with the visitor per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No later than 30 days prior to the candidacy visit | N/A |
| Programs reviewed under the 2022 EPAS submit: Benchmark 3 documents for BOA review (Volumes 1, 2, and 3) using the Required Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 3 Benchmark 3 documents to the BOA member visitor and the program’s CSWE accreditation specialist |
| Programs reviewed under the 2015 EPAS submit: Benchmark 3 documents for BOA review (Benchmark 1 Review Brief, and Volumes 1, 2, and 3) using the Optional Benchmark 1 Template for Volume 1 | No less than 30 days prior to the candidacy visit | The program emails the 4 Benchmark 3 documents to the BOA member visitor and the program’s CSWE accreditation specialist |
| The program’s primary contact and visitor jointly finalize the candidacy visit schedule per policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | No less than 1-week prior to the visit | N/A |
| Candidacy Visit 3 occurs For more information candidacy visits, review policy 5.9 Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | Between December 1, 2026 – February 28, 2027 | N/A |
| BOA Member Visitor submits the Candidacy Visit Report per policy 5.10 Candidacy Visits 1, 2, & 3 Reports in the Accreditation Policy Handbook | Within 2 weeks of the last day of the visit | The BOA visitor e-mails visit report to the program’s CSWE accreditation specialist to review, finalize, and forward to the program. |
| Program responds to the Candidacy Visit Report policy 5.11 Program Response to the Candidacy Visits 1, 2, & 3 in the Accreditation Policy Handbook | # Within 2 weeks of receiving the Candidacy Visit Report | The program e-mails the Program Response to the program’s CSWE accreditation specialist |
| BOA reviews the program’s Benchmark 3, Candidacy Visit Report, and Program Response to make a candidacy decision Decision types are detailed in policy 5.14 BOA Benchmark 3/Initial Accreditation Decisions in the Accreditation Policy Handbook | June 2027 BOA Meeting | N/A |
| All BOA letters are issued 30-days after the meeting | July 2027 | N/A |

Per policy 5.2 Retroactive Accredited Status in the Accreditation Policy Handbook), only students admitted to the social work program during or after the academic year in which the program is granted candidacy will be recognized as graduates from a CSWE-BOA accredited program, once the program achieves initial accreditation as granted by the Board of Accreditation (BOA).