Board of Accreditation (BOA)

Department of Social Work Accreditation (DOSWA)

Baccalaureate and Master’s Social Work Program Accreditation

Timetable for Reaffirmation | February 2030 Agenda

# Directions

Begin your reaffirmation planning process by identifying the program's next reaffirmation date. This date can be identified via the following ways:

- Listed in the Directory of Accredited Programs in the "Next Accreditation Review" date field.

- Stated in the program's last decision letter issued by the Board of Accreditation.

- Primary contacts may contact the program's CSWE accreditation specialist to verify. The program's primary contact is selected by each program and identified in the Directory of Accredited Programs.

To complete a blank timetable, input the program's next reaffirmation date into the last row on the table and work backwards from the final decision date to input all preceding due dates.

| Activity or Document | Date | Submission Instructions |
| --- | --- | --- |
| Strongly Recommended: Program participates in optional Reaffirmation Training | # 2-3 years before the program's next reaffirmation date (identified in the final row of this timetable). | N/A |
| Program begins drafting self-study by reviewing 2022 EPAS Accreditation Toolkit and Accreditation Policy Handbook All accreditation documents must align with the policy 4.7 Document Formatting & Submission Requirements | # 2-3 years before the program's next reaffirmation date (identified in the final row of this timetable). | N/A |
| $ CSWE invoices program for the Reaffirmation Eligibility Fee via email | # January 1, 2029 | Direct fee or invoice questions to feesaccred@cswe.org |
| Site Visit Planning Form opens and is available for program completion | # January 1, 2029 | Direct logistical site visit questions to the CSWE Accreditation Volunteer Manager |
| $ Program submits payment of the Reaffirmation Eligibility Fee | # February 1, 2029 | For instructions on payment, review Accreditation Fee Payment Options |
| Final date for the program to submit an optional Timetable Change Request Form to temporarily delay the current reaffirmation cycle Learn more in policy 4.6 Requesting an Extension or Timetable Change and policy 4.9 Program Changes in the Accreditation Policy Handbook | January 1, 2029 | If requesting a timetable change, email the required form to the program’s CSWE accreditation specialist |
| # Program completes the Site Visit Planning Form online | # February 1, 2029 | Complete the electronic form. |
| # Program submits the Reaffirmation Accreditation Eligibility Application | # March 1, 2029 Reaffirmation Eligibility Fee must be received prior to application approval Applications are reviewed within 30 days of this due date; early submissions may not be reviewed until after March 1, 2029 CSWE accreditation staff may request clarifying information | Email the application to the accreditation@cswe.org |
| Program will be reviewed under the 2022 EPAS. Program submits: The Reaffirmation Self-Study Volumes 1, 2, and 3 All accreditation documents must align with the policy 4.7 Document Formatting & Submission Requirements | April 1, 2029 | Email the three (3) self-study documents (volumes 1-3) to the program’s CSWE accreditation specialist |
| CSWE Accreditation Volunteer Manager assigns a site visitor and confirms the visit date via email All visit planning is completed directly between the program and visitor | By April 1, 2029 | Direct logistical questions to the CSWE Accreditation Volunteer Manager Direct standard-related questions to the program’s CSWE accreditation specialist |
| $ CSWE invoices program for the Reaffirmation Fee via email | June 1, 2029 | Direct fee or invoice questions to feesaccred@cswe.org |
| BOA reviews the program’s Reaffirmation Self-study and issues the Letter of Instruction (LOI) to the site visitor All BOA letters are issued 30-days after the meeting BOA decisions are publicly posted on the CSWE BOA Decision webpage 30-days after the meeting | June 2029 BOA Meeting | N/A |
| $ Program submits payment of the Reaffirmation Fee | July 1, 2029 | For instructions on payment, review Accreditation Fee Payment Options |
| Site visit occurs For more information candidacy visits, review policy 6.6 Site Visit | Between September 15, 2029 – October 15, 2029 | N/A |
| # Site visitor aligns report with policy 6.7 Site Visit Report and submits the Site Visit Report to the program’s CSWE accreditation specialist via email | Within two (2) weeks of the last day of the visit | Site visitor e-mails visit report to the program’s CSWE accreditation specialist to review, finalize, and forward to the program |
| # CSWE accreditation staff review, finalize, and issue the Site Visit Report to the program via email with instructions to complete next steps | CSWE accreditation staff may request clarifying information Please allow time for CSWE accreditation staff to review the report and request clarifications (if needed) | Program’s CSWE accreditation specialist reviews, finalizes, and forwards the visit report to the program |
| Using the required template and policy 6.8 Program Response to the Site Visit Report, program submits Program Response to the Site Visit Report All accreditation documents must align with the policy 4.7 Document Formatting & Submission Requirements | Within two (2) weeks of the receiving the Site Visit Report | The program e-mails the Program Response to the Site Visit Report to the program’s CSWE accreditation specialist |
| # BOA reviews the Letter of Instruction (LOI) to the site visitor, Site Visit Report, and Program Response # BOA issues a reaffirmation determination All BOA decision letters are issued 30-days after the meeting BOA decisions are publicly posted on the CSWE BOA Decision webpage 30-days after the meeting Learn more about reaffirmation decision types in policy 6.9 BOA Reaffirmation Decisions and BOA-issued letters in policy 3.13 Decision Letters in the Accreditation Policy Handbook | February 2030 BOA Meeting | N/A |